## Retest of 42 cases
Test ID | Profile | Screen | Status v3 | Severity v3 | Retest | Retest note / what remains | Dev note (07 Oct 2026)
WEB-S-01 | Student | Sign-in | Fail | Major | Pass | One sign-in page with profile list and pre-filled demo credentials: OK; persona cards gone; protected URLs redirect to the login page.
WEB-S-02 | Student | Course menu | Pass | — | Pass | Unchanged, still OK.
WEB-S-03 | Student | Final Quiz (Exercise 4) | Fail | Critical | Pass | Badge now "Open"; after an attempt the quiz is locked ("Quiz final terminé") until the teacher allows a retry.
WEB-S-04 | Student | Final Quiz (Exercise 4) | Fail | Critical | Pass | 8 Safety questions out of 20 shown in the header; quit warning present.
WEB-S-05 | Student / Teacher | Final Quiz / Exercise 4 content | Fail | Major | Pass | FR verified on Tour, Identification, Startup, Repair, Catalogue, Results, teacher pages. The student Final Quiz was only played in EN.
WEB-S-06 | Student | Identification (Exercise 1) | Fail | Major | Pass | Fixed - verified on the new build.
WEB-S-07 | Student | Identification (Exercise 1) | Fail | Critical | Pass | Labels hidden during the question, hint inside the card, neutral selection, explanation + audio after each answer, full results page. Layout of the results page: see IDENT-3 / RES-1.
WEB-S-08 | Student | Startup Procedure (Exercise 2) | Fail | Minor | Pass | Only completed steps shown, 2-level hint, results page. Panel overflow from step 10: see START-1.
WEB-S-09 | Teacher | Startup Procedure — step names consistency | Fail | Major | Pass | Fixed - verified on the new build.
WEB-S-10 | Student | Repair (Exercise 3) | Fail | Major | Pass | Toolbox, reference sheet (draft content), foreign-body scenario, results. Improvements: REP-1 to REP-5.
WEB-S-11 | Student | Repair (Exercise 3) | Fail | Major | Pass | Fixed - verified on the new build.
WEB-S-12 | Student | Repair (Exercise 3) | Fail | Minor | Pass | Fixed - verified on the new build.
WEB-S-13 | Student | My Results | Fail | Minor | Pass | All attempts clickable with date, device, duration; FR OK. Improvements: RESULTS-1 to RESULTS-3.
WEB-S-14 | Student | Component Catalogue | Fail | Major | Pass | 32 components, 3D zoom + component card, back to the same position verified. Improvements: CAT-1 to CAT-3.
WEB-S-15 | Student | Course menu — header bar | Fail | Minor | Pass | User badge with EN/FR + log out, course name, global mute, logo -> menu.
WEB-S-16 | Student | Guided Tour | Fail | Major | Partial | Audio, Play/Replay, Previous, end screen, breadcrumb, Exit: OK. Still a 2D schematic (see TOUR-2) and "Next" is clickable before the narration ends (first run). | Dev: still the 2D schematic (TOUR-2). "Next" before the end of the narration is unchanged: the demo student is seeded as having already completed the tour, which unlocks it; a new student is blocked.
WEB-S-17 | Student | Course menu — exercise score badge | Fail | Minor | Pass | Fixed - verified on the new build.
WEB-S-18 | Student | Guided Tour, Identification, Startup Procedure, Repair, Final Quiz | Fail | Major | Pass | Exit and save / without saving + Resume; Final Quiz quit warning.
WEB-S-19 | Student | Identification, Startup Procedure, Repair, Final Quiz | Fail | Major | Pass | Fixed - verified on the new build.
WEB-T-01 | Teacher | Lesson Preview (list) | Fail | Major | Partial | Preview banner, "back to preview" and exit dialog OK on Tour, Identification, Startup, Repair, Final Quiz, Exploded view. The Component Catalog preview has no banner and its "Course Menu" breadcrumb goes to My Classes. See PREV-1/2/4. | Dev: fixed with PREV-1 / PREV-5 (same preview chrome on the catalogue, no "Quitter" button).
VR-01 | Student | Onboarding ('Premiers pas') | Fail | Major | Pass | Hand-tracking onboarding with pinch / grab practice, controllers as fallback, replay gestures in the VR menu.
VR-02 | Student | Course menu (VR) | Fail | Major | Pass | Tour end screen, level-2 hint halo + arrow, single Menu button, short VR results, locked Final Quiz re-checked in VR.
DASH-T-01 | Teacher | My Classes | Fail | Minor | Pass | Year dropdown, working filters, bell, (i) tooltips. Not verified: KPI tiles clickable as filters. Table scrolls horizontally at 1024 px: TCH-1.
DASH-T-02 | Teacher | Class Roster (Students tab) | Fail | Minor | Pass | Fixed - verified on the new build.
DASH-T-03 | Teacher | Assignments tab | Fail | Major | Pass | Fixed - verified on the new build.
DASH-T-04 | Teacher | Scoring Rubric tab | Fail | Major | Pass | Fixed - verified on the new build.
DASH-T-05 | Teacher | Final Quiz tab (Exercise 4 settings) | Fail | Major | Pass | Single bank of 32 questions, random / fixed set, pickers, add-question dialog with 3D / image / multi-answer / explanation. Not verified: warning when < 5 Safety.
DASH-T-06 | Teacher | Student detail | Fail | Minor | Pass | Fixed - verified on the new build.
DASH-T-07 | Teacher | Live Sessions / Live view | Pass | — | Pass | Fixed - verified on the new build.
DASH-A-01 | Client Admin | Users | Fail | Major | Pass | Fixed - verified on the new build.
DASH-A-02 | Client Admin | Users | Pass | — | Pass | Fixed - verified on the new build.
DASH-A-03 | Client Admin | Classes | Fail | Minor | Pass | Fixed - verified on the new build.
DASH-A-04 | Client Admin | Audit Log | Fail | Minor | Pass | Filters, search, sort, pagination, CSV button. English values remain in the FR UI (AUD-1); filters not aligned (AUD-4).
DASH-A-05 | Client Admin | Headsets | Fail | Minor | Pass | Fixed - verified on the new build.
DASH-A-06 | Client Admin | Settings | Fail | Minor | Partial | File upload field present (JPEG/PNG/SVG, 500 KB). An actual upload and the logo in the header were NOT verified. | Dev: not touched in this pass — real upload and logo in the header still to verify.
PLAT-01 | COMIM Admin | Overview | Fail | Minor | Pass | Fixed - verified on the new build.
PLAT-02 | COMIM Admin | Establishments → New establishment | Pass | — | Pass | Fixed - verified on the new build.
PLAT-03 | COMIM Admin | Establishments | Fail | Minor | Pass | Fixed - verified on the new build.
PLAT-04 | COMIM Admin | Audit Log | Fail | Minor | Pass | Fixed - verified on the new build.
PLAT-05 | COMIM Admin | Licences & Features | Fail | Major | Pass | Fixed - verified on the new build.
PLAT-06 | COMIM Admin | Usage Reports | Fail | Minor | Pass | Consistent demo data, CSV / PDF export, sortable columns. Rework requested: PLAT-U1.
PLAT-07 | All roles | Header — search | Fail | Major | Pass | Fixed - verified on the new build.

## To fix
ID | Area | Profile | Priority | What's wrong | What to change | Design (Claude Design) | Status | Dev status | Dev note (07 Oct 2026)
AUTH-1 | Sign-in | All | Minor | Two helper sentences appear on the login page: "Une seule page de connexion pour tous les profils." and "Identifiants de démo pour ce profil : student / student". | Remove both sentences (FR and EN). |  | Validated | Done | Both helper sentences removed from the sign-in page (FR and EN).
HOME-1 | Student home | Student | Minor | Tiles are unevenly spaced (gaps 12 / 53 / 0 px: "Mes résultats" and "Catalogue" touch). | Same spacing between ALL tiles. |  | Validated | Done | Tiles are in one flex column with a single 12 px gap. Measured in the browser: 12 px between all 8 tiles, all 720 px wide.
HOME-5 | Student home | Student | Minor | The "Enregistré le… / Recommencer / Reprendre" block is a separate strip, narrower than its tile (696 vs 720 px), glued below it. | Improve the delimitation between the exercise tile and the saved block. Ask for confirmation before "Recommencer" (saved progress will be lost). |  | Validated | Done | The saved block is now part of its tile (same card and width, divider in between). "Recommencer" asks for confirmation before the saved progress is deleted.
TOUR-2 | All 3D scenes | All | Major | All scenes (Tour, Identification, Startup, Repair, Catalogue, Exploded view) are 2D SVG schematics. | The final delivery must be the 3D model; the 2D schematic is while the 3D is being created. |  | Validated | Not done | Needs the real 3D model. All scenes are still the 2D schematic; the scene component is isolated so the 3D view can replace it.
TOUR-3 | Guided Tour / all audio | Student | Major | Mute then unmute: the voice never comes back (unmute does not call the speech engine); | on unmute of the voici is not finished yet, it should relaunch the sound. |  | Validated | Done | Unmuting while the narration is running relaunches the voice from the current sentence. The audio buttons also unmute and play in one click.
TOUR-4 | All exercise screens | All | Major | The 3D area is not centred and the page scrolls: at 1280x620 content is 628 px for 620 px (3D only 470 px high); at 1440x780 the schematic touches the edges ("Purgeur d'air" at the top, "Vers caisse d'eau dou…" cut on the left) and the +/- buttons cover the bottom-left corner; at 1024x768 it sits top-left. | Responsive: the scene fits its container (contain) with an inner margin, centred; the page is exactly the screen height with no page scroll at any size or aspect ratio (test 1024x768, 1280x620, 1440x780, 1920x1080); a side panel scrolls on its own if needed. Same layout for Identification, Startup, Repair. |  | Validated | Done | Exercise screens are exactly the screen height from 1024 px wide (no page scroll, side panels scroll on their own). The scene is contained and centred with an inner margin; zoom controls sit under the scene, not on it. Checked at 1280x620 (document height = 620) on Startup, Identification and Repair; 1024x768, 1440x780 and 1920x1080 not measured.
TOUR-5 | Audio | Student | Minor | No visible audio state. | Indicator "playing / paused / muted" next to the sound button. |  | Validated | Done | State chip next to the sound button of the narration: playing / paused / finished / muted. The header mute button shows "Muet" when muted.
TOUR-1 | Narration audio | All | Major | The voice is the browser speech synthesis (Web Speech API): no audio files, voice depends on the OS / browser (likely absent or poor in the Quest browser); the progress bar is simulated (duration = words / 2.6). | Target on the delivery : pre-generate narration, hints and explanations per language (FR + EN) with ElevenLabs or Azure Neural TTS (or any other tools with humain voice), stored as files; real progress bar and word-timestamps for the highlight; same files in VR. |  | Validated | Not done | Needs pre-generated narration files (ElevenLabs / Azure). Still browser speech synthesis with a simulated progress bar. Voice volume is now adjustable.
ZOOM-1 | All 3D scenes | All | Major | Zoom is static: +/- zoom around a fixed centre, max 3x; drag does not pan, the wheel does not zoom. At 3x only 6 of the 22 clickable parts of the Startup scene can ever be brought into view (16 unreachable). | Pan by drag (mouse and touch) within bounds; wheel / pinch zoom centred on the cursor; double-click or a "Cibler la pièce" button zooms and centres on the part; max zoom 5-6x; +/- disabled at limits; visible "recentrer" button. 3D delivery: orbit + pan + zoom + auto-frame. |  | Validated | Done | Drag to pan (mouse and touch) within bounds, wheel and pinch zoom centred on the cursor, max 6x, +/- disabled at the limits, visible "Recentrer" button, "Cibler la pièce" button, double-click zooms (on the background only in exercises, where a double-click on a part would count as two answers). 3D orbit comes with the 3D delivery.
ZOOM-3 | Identification | Student | Minor | The highlighted part is small on a full schematic and the zoom cannot reach it. | Auto-frame the highlighted part when an Identification question is displayed. |  | Validated | Done | The highlighted part is framed automatically (zoom + centre) for each Identification question. Verified in the browser.
REP-1 | Repair | Student | Major | The only sound is the browser voice: no engine-room ambience or effects. | Ambient engine-room loop and event sounds (alarm, valve, wrench, pump start/stop, vacuum), state-dependent, ducked under the voice, global mute + separate voice / ambience volume, spatialised in VR. Delivered with the 3D scene. |  | Validated | Partial | Engine-room ambience loop and event sounds (alarm, valve, wrench, lockout, pump start/stop, vacuum) are in, state-dependent, ducked under the voice, with global mute and separate voice / ambience sliders. They are SYNTHESISED placeholders: recorded audio and VR spatialisation come with the 3D package.
REP-2 | Repair | Student | Major | The red alarm badge and a modal describing the fault are shown from the first frame. | Start in normal operation (normal values, ambience); after about 3 s (configurable 3-5 s, longer in VR) trigger the alarm; replace the modal by a short briefing. |  | Validated | Done | Repair starts in normal operation; the alarm trips after 3 s (5 s in VR, configurable constant). The modal is replaced by a short briefing banner in the side panel.
REP-3 | Repair | Student | Major | The statement gives cause and action: "Un débris passé à travers un filtre endommagé obstrue la buse de l'éjecteur. Localisez et extrayez le corps étranger." | Give symptoms only: "Alarme niveau de saumure haut. Le débit d'eau douce baisse et le vide se dégrade. Diagnostiquez la cause puis intervenez." Add an explicit diagnosis step (choose the probable cause among 3-4: blocked ejector nozzle / pump failure / air leak / low jacket-water flow) validated before the repair steps. |  | Validated | Done | Statement gives symptoms only (wording from the sheet). Explicit diagnosis step with 4 causes after the two observation steps, validated before the repair steps. The diagnosis appears in the correction but does not count in the rubric score.
REP-4 | Repair | Student | Minor | Toolbox = 7 text buttons with small generic icons, no tooltip, inconsistent sizes (4 x 48 px, 3 x 34 px), last tool alone on its row. | Grid of equal icon tiles (large illustrated icons / 3D thumbnails), name below, tooltip on hover / focus (name + one line "when to use"), selected tool highlighted and shown on the cursor; in VR the tools are 3D objects on a bench. |  | Validated | Done | Toolbox is a 4x2 grid of equal tiles (8 x 86x84 px measured), larger icons, name below, tooltip with name + "when to use", selected tool highlighted and shown on the cursor. Icons are line icons, not illustrated / 3D thumbnails. VR bench with 3D tools comes with the XR package.
REP-5 | Repair | Student | Major | No numeric value is shown anywhere in Repair; "Main" mixes observe and operate. | New tool "Contrôle visuel" (magnifier / eye), separate from the hand: pointing an instrument shows its reading (vacuum %, driving pressure bar, brine level, flow, salinity), normal then degraded after the fault; values consistent with the technical sheet (3.5-4.5 bar, vacuum >= 90 %). |  | Validated | Done | New tool "Contrôle visuel", separate from the hand. Pointing an instrument shows its reading (vacuum, driving pressure, brine level, flow, salinity): normal, then degraded after the fault, then stopped. Values consistent with the technical sheet.
CAT-1 | Component catalogue | Student | Minor | Text-only table (32 rows, page 2669 px), no picture, no filter; "Définition" column sortable. | Grid / list with a small render per part, filter chips by zone or type (valve, pump, instrument), keep search, sort on name only. |  | Validated | Done | Card grid with a small render of each part, filter chips by type (shell and exchangers / valves / pumps and ejector / instruments / other), search kept, sort on name only.
CAT-2 | Component catalogue | Student | Major | Technical notes spoil the exercises: ejector nozzle "Un corps étranger ici bloque le vide…", suction valve "Première vanne ouverte…", vacuum gauge "Doit atteindre 90 % en 15 s", air vent "Fermé avant de faire le vide". | Neutral notes (what it is, where, normal range) with no procedure order or fault cause; catalogue not reachable during a Final Quiz attempt. |  | Validated | Done | All 32 notes rewritten as neutral notes (what, where, normal range). The catalogue is closed while a Final Quiz attempt is in progress (page and header search).
CAT-3 | Component catalogue | Student | Minor | The same text is "Note technique" in the table and "Indice / Hint" on the component card, and shown without being asked. | Use one label; show it as a note, not a hint. |  | Validated | Done | One label "Note technique" in the list, on the component card and in the Exploded view, shown as a note.
RESULTS-1 | My Results | Student | Minor | Attempts are listed oldest first (latest at the bottom); 17 attempts = 1744 px, unlimited growth. | Newest first; show 3 attempts then "Voir tout/See all". |  | Validated | Done | Newest first; 3 attempts shown, then "Voir tout".
RESULTS-2 | My Results | Student | Minor | No summary and no filter. | Header per exercise: best score, last score, number of attempts; filters Exercise / Device (Web, VR). |  | Validated | Done | Header per exercise with best score, last score and number of attempts; Exercise and Device filters.
RESULTS-3 | My Results | Student | Minor | Pass / fail only by colour (orange / green), pass mark not shown. | Word badges "Réussi" / "À revoir" / "Abandonnée" and the pass mark (70 %) in the header. |  | Validated | Done | Word badges "Réussi" / "À revoir" / "Abandonnée" and the pass mark (70 %) in the header.
GLB-1 | Side menu (all profiles) | Teacher / Client Admin / COMIM Admin | Major | After "Réduire le menu", any click on a menu item reopens it (250 px again); no storage key for the state, it is lost on every page change and reload. | Persist the open / closed state per user and device and keep it across navigation and reload. |  | Validated | Done | Open / closed state of the side menu is stored per user and device and kept across navigation and reload.
QZT-1 | Teacher > class > Quiz final | Teacher | Minor | The settings card is titled "Règles de jeu" ("Play rules"), the only game vocabulary of the app. | Rename to "Paramètres du quiz" (EN "Quiz settings"). use the new UI design proposed in the column G | https://claude.ai/artifact/EQfKbnpQjVgEngbVw1r4oX | Validated | Done | Card renamed "Paramètres du quiz" / "Quiz settings". Built from the written description: the Claude Design artifact could not be opened from the dev account (not shared), so the layout may differ from the mock-up.
QZT-2 | Teacher > class > Quiz final | Teacher | Major | Two cards side by side (question bank 498 px ¦ settings 452 px); the bank list duplicates the "Banque de questions" page. | Single column: "Paramètres du quiz" first (scope, draw mode, duration, skip switch on one row + "Enregistrer et ouvrir le quiz"), then a bank summary with an optional accordion "Voir les questions" and a "manage bank" button. Student picker for "Élèves sélectionnés" / "Nouvelle tentative individuelle". use the new UI design proposed in the column G | https://claude.ai/artifact/EQfKbnpQjVgEngbVw1r4oX | Validated | Done | Single column: settings first (scope, draw mode, duration, skip switch on one row + "Enregistrer et ouvrir le quiz"), then a bank summary with the "Voir les questions" accordion and a "Gérer la banque" button. Student picker for selected students / individual retry. Built from the written description: the Claude Design artifact could not be opened from the dev account (not shared), so the layout may differ from the mock-up.
QZ-0 | Teacher > class > Quiz final | Teacher | Minor | No confirmation after "Enregistrer et ouvrir le quiz". | Confirmation banner "Quiz ouvert pour N élèves" with a link to the Students tab (as in the mock-up). | https://claude.ai/artifact/EQfKbnpQjVgEngbVw1r4oX | Validated | Done | Confirmation banner "Quiz ouvert pour N élèves" with a link to the Students tab. Built from the written description: the Claude Design artifact could not be opened from the dev account (not shared), so the layout may differ from the mock-up.
QB-A | Question bank (Teacher + Client Admin) | Teacher / Client Admin | Minor | Badge "COMIM" is unexplained and ties the default questions to the vendor name. | Rename to "Par défaut" / "Default" (filter "Toutes les sources / Par défaut / École", header counters); tooltip: provided bank, not editable. |  | Validated | Done | Badge renamed "Par défaut" / "Default" with a tooltip (provided bank, not editable); source filter and header counters updated.
QB-B | Question bank (Teacher + Client Admin) | Teacher / Client Admin | Major | No edit, duplicate, disable or delete control on any question (only "Ajouter une question"). | Row actions: Modifier (author only), Dupliquer (everyone), Activer / Désactiver, Supprimer (author only), Aperçu élève; bulk actions with row checkboxes; badge "Désactivée" + filter Statut; default questions are not editable by anyone: "Dupliquer et modifier" creates a school question. Editing uses the "Ajouter une question" form. |  | Validated | Done | Row actions: Aperçu élève, Modifier (author only), Dupliquer (everyone; "Dupliquer et modifier" on a default question creates a school question), Activer / Désactiver, Supprimer (author or admin). Row checkboxes with bulk enable / disable, "Désactivée" badge, Status filter. Editing uses the add-question form.
QB-C | Question bank (Teacher + Client Admin) | Teacher / Client Admin | Major | Risk of a quiz that cannot generate 20 questions. | Never allow fewer than 20 ACTIVE questions (per class too): "Désactiver" is greyed with a tooltip "Minimum 20 questions actives", bulk disable stops at the limit with a message, counter "Actives 20 / 32 (minimum 20)". Safety minimum is NOT blocking: the quiz always generates its 20 questions with up to 5 Safety if available (label "Aléatoire - 20 questions dont 5 Sécurité si disponibles"), non-blocking warning only. |  | Validated | Done | A class can never have fewer than 20 active questions: "Désactiver" is greyed with the tooltip, bulk disable stops at the limit with a message, counter "Actives n / 32 (minimum 20)". The Safety minimum is a non-blocking warning; random mode label updated.
QB-D | Question bank (Teacher + Client Admin) | Teacher / Client Admin | Major | Rights and sharing of school questions are undefined. | Admin: school-wide (disable for the school or per class, delete). Teacher: disable only for own classes. A teacher's question is visible to the whole school with the author's name ("École · Nom") but NEVER auto-activated in other teachers' classes (opt-in; indicator "Activée dans : 2A, 3B"). Only the author edits; the admin may disable school-wide and delete, not rewrite. Author edit = immediate effect where active (past attempts keep their snapshot). Delete = blocked while any class would fall under 20 active questions (message names the class). All changes written to the audit log. |  | Validated | Done | Admin acts school-wide or per class, teacher only on own classes. A teacher question is visible to all with the author name and is active only in classes that opted in ("Activée dans : ..."). Only the author edits; the admin can disable and delete. Delete is blocked, naming the class, if it would fall under 20. All changes are written to the audit log.
QB-E | Client Admin | Client Admin | Minor | The admin reaches the bank only through Paramètres > "Ouvrir", which opens /teacher/question-bank (teacher URL, no menu entry, nothing highlighted). The session stays admin (role guard works). | Dedicated route /admin/questions and a "Banque de questions" entry in the admin menu, same shared page. |  | Validated | Done | Route /admin/questions with a "Banque de questions" entry in the admin menu (highlighted). /teacher/question-bank is teacher-only.
PREV-1 | Course preview (teacher) | Teacher | Minor | Three exits (banner link, "Quitter" with a useless confirmation, breadcrumb); wording "aperçu des leçons" vs "Aperçu du cours". | Same chrome on every previewed module as the Exploded view: banner "Mode aperçu - aucune note enregistrée" + "Retour à l'aperçu du cours" + breadcrumb "Aperçu du cours > module"; no "Quitter" button; wording "Aperçu du cours" / "Course preview". |  | Validated | Done | Same chrome on every previewed module: banner "Mode aperçu — aucune note enregistrée" + "Retour à l'aperçu du cours" + breadcrumb "Aperçu du cours > module". No "Quitter" button and no confirmation in preview. Wording "Aperçu du cours" / "Course preview".
EXPL-1 | Exploded view | Student | Minor | The Exploded view exists in the teacher preview and the VR menu but not in the student web menu. | Add "Vue éclatée" to the student web course menu. |  | Validated | Done | "Vue éclatée" added to the student web course menu (/student/exploded).
EXPL-2 | Exploded view | All | Minor | Right panel is an empty text "Cliquez sur une pièce pour afficher sa fiche". | Show the clickable, searchable list of parts; a click on the list or the scene shows the card. |  | Validated | Done | Right panel is a searchable list of the parts; a click on the list or on the scene shows the card.
ADM-1 | Client Admin > Utilisateurs | Client Admin | Major | Rows and names are not clickable; only a pencil opening an edit pop-up. | User detail page /admin/users/<id>. Student: identity, status, class + track (class link), teachers, progress per exercise and Final Quiz (status, score, attempts), devices, recent attempts (reuse the teacher student sheet), actions Modifier / Changer de classe (logged) / Désactiver. Teacher: classes taught (headcount, progress, quiz opened), last login, delegation, recent actions, actions Modifier / Affecter classes / Désactiver. List: name = link, clickable row, columns Filière / Statut / Dernière connexion; pencil kept. |  | Validated | Done | User detail page /admin/users/<id>. Student: identity, status, class + track, teachers, progress per exercise and Final Quiz, devices, recent attempts, recent activity; actions Modifier / Changer de classe (logged) / Désactiver. Teacher: classes taught, last login, delegation, recent actions; actions Modifier / Affecter classes / Désactiver. List: name is a link, row clickable, columns Filière / Statut / Dernière connexion, pencil kept. Deactivation is a status flag in the demo data.
ADM-2 | Client Admin > Classes | Client Admin | Major | A class cannot be opened; only a pencil edit pop-up. | Class detail page /admin/classes/<id>: header (name, track, year, teachers as links, headcount, progress, status), students (link to user page, add / remove / move), assigned content and completion, Final Quiz stats, assigned headsets, recent activity; actions Modifier / Affecter enseignants / Archiver ou clôturer l'année / Transférer à l'année suivante. |  | Validated | Done | Class detail page /admin/classes/<id>: header, students (links, add, move), assigned content and completion, Final Quiz stats, assigned headsets, recent activity; actions Modifier / Affecter enseignants / Archiver / Transférer à l'année suivante. No "remove from class" action: a student is moved, never left without a class.
ADM-3 | Client Admin > Casques | Client Admin | Major | No page per headset; only a pencil edit pop-up. | Headset detail page /admin/headsets/<id>: identity and status, current use (with "Voir en direct"), assigned classes, usage, session history, pairing history; actions Modifier / Désappairer / Régénérer le code d'appairage. |  | Validated | Done | Headset detail page /admin/headsets/<id>: identity and status, current use with "Voir en direct", assigned classes, usage, session history, pairing history; actions Modifier / Désappairer / Régénérer le code. Session history is demo data.
ADM-4 | Admin tools (rule) | Client Admin / COMIM Admin | Minor | Lists open nothing. | General rule: every listed entity opens a detail page (users, classes, headsets; to evaluate for COMIM Admin licences and audit entries). Pencil stays as quick edit. |  | Validated | Partial | Done for users, classes and headsets (rows and names open the detail page, pencil kept). Not done for COMIM Admin licences and audit entries, which the sheet left "to evaluate".
PLAT-U1 | COMIM Admin > Rapports d'usage | COMIM Admin | Major | The page is 4 totals plus a per-school table that duplicates the establishment sheet; no trend, no breakdown. | Cross-establishment dashboard with 4 tabs: Vue d'ensemble (4 KPI, sessions chart, Web / VR split, "À surveiller"), Apprentissage et contenu (exercises per module, pass rate, hardest questions / steps, hint usage), Établissements et casques (seat usage, fleet, ranking with links), Rapports SQL. Filters: period, plan. Export CSV / PDF. Per-school detail stays in the establishment sheet. | https://claude.ai/artifact/V5YStRKtoaqrxrME6fcDRp | Validated | Done | Cross-establishment dashboard with 4 tabs (Vue d'ensemble, Apprentissage et contenu, Établissements et casques, Rapports SQL), period and plan filters, CSV / PDF export. Learning figures (hardest questions / steps, hints) are demo data. Built from the written description: the Claude Design artifact could not be opened from the dev account (not shared), so the layout may differ from the mock-up.
PLAT-U2 | COMIM Admin > Rapports d'usage | COMIM Admin | Major | Custom SQL exists only per establishment. | Custom reports (SQL) across ALL establishments: name, scope (all / selection), SQL editor with read-only / 10 s / 1 000 rows limits, parameters (:periode_debut, :periode_fin), list of available tables, run -> table or bars, CSV export, schedule (manual / weekly / monthly) with e-mail, visibility, save; each run logged in the audit log. (Read as "par SQL customisé": to confirm.) | https://claude.ai/artifact/V5YStRKtoaqrxrME6fcDRp | Validated | Done | SQL reports across all establishments: name, scope (all / selection), editor with read-only / 10 s / 1 000 rows limits, :periode_debut / :periode_fin, table list, run -> table or bars, CSV export, schedule with e-mail, visibility, save. Each run is logged in the audit log (verified). The query result is simulated. Built from the written description: the Claude Design artifact could not be opened from the dev account (not shared), so the layout may differ from the mock-up.
AUD-3 | Audit log (both) | Client Admin / COMIM Admin | Minor | New actions of this retest are not covered. | Add audit actions: question created / modified / duplicated / disabled / deleted, user deactivated or class changed, class archived / transferred, headset unpaired, track removed, delegation toggled, settings saved. |  | Validated | Done | New audit actions: question created / modified / duplicated / disabled / enabled / deleted, user deactivated / reactivated, class changed, class archived / transferred, headset unpaired, pairing code regenerated, track added / removed, delegation toggled, settings saved, SQL report run.
AUD-4 | Audit log (both) | Client Admin / COMIM Admin | Minor | Filters misaligned (widths 170 / 280 / 152 / 141 / 147 px at 36 px high, the period select wraps alone, "Exporter CSV" 42 px high), no visible labels. | One aligned grid: label above each field, all 44 px, search spanning 2 columns, entry count + "Réinitialiser les filtres" under it, Export CSV in the title card. COMIM Admin adds Établissement and Origine. | https://claude.ai/artifact/LrdaNRAZ64k2KKeh9nBUJi | Validated | Done | One aligned grid per the mock-up: label above each field, all 44 px high (measured), search spanning 2 columns, entry count + "Réinitialiser les filtres" underneath, Export CSV in the title card. COMIM Admin adds Établissement and Origine.
AUD-5 | Audit log (both) | Client Admin / COMIM Admin | Major | Modified values are free text ("Final Quiz: 75% → 80%"). | Structured columns: Date / Auteur (+ profil) / Action / Cible (link) / Modification avant → après. One change inline (before grey struck, after green); several = "N champs modifiés ▸" expandable Champ / Avant / Après; justification shown under the row. | https://claude.ai/artifact/LrdaNRAZ64k2KKeh9nBUJi | Validated | Done | Structured columns Date / Auteur (+ profil) / Action / Cible (link) / Modification avant → après. One change inline (before struck grey, after green); several = "N champs modifiés" expandable Champ / Avant / Après; justification under the row.
VR-3 | VR onboarding | Student | Major | The onboarding hand is ONE hand-coded SVG of rounded rectangles (square palm + finger bars) reused for all 5 steps, including "Regardez autour de vous" (a head turn); placeholder-grade, no asset. | One distinct, properly illustrated pictogram per gesture (head turn, open palm up, pinch, grab, point) in the Quest hand-tracking style, or short looping clips / "ghost hands"; in the headset show the player's own tracked hands plus a ghost-hand demonstration; keep the hold-to-validate practice circle and add clear feedback (halo + sound). Deliver with the 3D / XR package. |  | Validated | Not done | Needs illustrated gesture assets / ghost-hand clips. To deliver with the 3D / XR package.
VR-7 | VR (all modules) | Student | Major | Pinch target size and reading size cannot be validated in a browser simulation. | Define minimum pinch-target and text sizes in the XR brief and run an acceptance test on a real Quest 2 and Quest 3. |  | Validated | Not done | Needs an acceptance test on a real Quest 2 and Quest 3; cannot be done in the browser build.
IDENT-1 | Identification | Student | Minor | User: the question card is too condensed. Measured at 1024x768: card 398 px wide (39 %), answers 46 px high only 8 px apart, title / hint / progress 11-12 px apart, "Écouter" squeezed on the title row. | Card about 45 % wide (min 440 px), answers 12-16 px apart with more padding, audio + hint on their own row under the question, thin progress bar at the top, 24 px before the confirm button. |  | To confirm | Done | Card 45 % wide (min 440 px; 520 px measured at 1280), answers 54 px high and 14 px apart, audio + hint on their own row under the question, thin progress bar at the top, 24 px before the confirm button. Implemented as written although the row is "To confirm".
IDENT-2 | Identification | Student | Major | User: the same part must not be asked for both Name and Function in one exercise (the Name explanation gives the function and vice versa). Today: 4 parts x 2 questions, fixed order. | 8 DIFFERENT parts per attempt drawn at random from the 32 components (as in the spec), 4 Name + 4 Function mixed, each part once; keep the Name / Function score split. |  | To confirm | Done | 8 different parts per attempt drawn at random, 4 Name + 4 Function mixed, each part once, Name / Function split kept. The 2D schematic has 22 clickable parts for the 32 components, so sub-components highlight their parent part (e.g. the ejector). Implemented as written although the row is "To confirm".
IDENT-3 / RES-1 | Results pages (student + teacher) | Student / Teacher | Major | User: "Pièces à revoir" next to the 3D image leaves an empty band: Identification 146 px, Startup 932 px (13 parts, right column 1292 px vs 360 px, page 3321 px), Repair not yet. Pages are very long. | One shared results layout: 3D sticky (or fixed-height panel), "parts to review" merged into the question-by-question correction (click = highlight in 3D), max 3-4 shown + "voir tout", correct answers collapsed. |  | To confirm | Done | One shared results layout (student and teacher): sticky machine panel, parts to review merged into the correction (click = highlight and frame the part), 4 lines shown + "voir tout", correct answers collapsed. Implemented as written although the row is "To confirm".
HOME-6 | Student home | Student | Minor | The "Mes résultats" and "Catalogue des composants" tiles touch each other (0 px gap, the shadows overlap) while the other tiles are 12 px apart. | Add the same gap (12-16 px) between these two tiles as between all the other tiles of the course menu. |  | Validated | Done | Same 12 px gap between "Mes résultats" and "Catalogue" as between all other tiles (measured).
START-1 | Startup Procedure | Student | Major | The right panel overflows as steps accumulate: at step 11/13 the page is 935 px for 768 px; the "Correct" feedback and "Étape suivante" fall below the fold; the hint button is at y = 880. | Three zones: header (counter + progress) / scrollable step list that follows the current step (or last 3 steps + "voir les précédentes") / pinned footer with feedback, "Étape suivante" and hint; the page never scrolls. |  | Validated | Done | Three zones: header (counter + progress) / step list that scrolls and follows the current step / pinned footer with feedback, "Étape suivante" and hint. The page does not scroll (checked at 1280x620).
START-4 | All schematics | Student | Minor | Labels overlap ("Tableau de commande / Journal machine", "Manomètre de l'éjecteur" crossed by a pipe, "Débitmètre / électrovanne / salinomètre"). | Solved by the real 3D with a proper label layout. |  | Validated | Not done | To be solved by the real 3D label layout; labels of the 2D schematic are unchanged.
HDR-1 | Student header bell | Student | Minor | Notifications show ISO dates ("pour le 2026-09-22") and truncated text; 4 past-due assignments unread. | Localised dates, wider popover. |  | Validated | Done | Localised dates in notifications, popover widened to 440 px, text no longer truncated. Exercises already done are no longer notified; past-due ones are labelled "Exercice en retard".
TCH-2 | Teacher > class > Élèves | Teacher | Minor | Quiz column shows only a chip (Verrouillé / Ouvert / Terminé); no score, attempts, search, filter or export. | Columns "Score du quiz" (80 % · Réussi) and "Tentatives"; rename "Verrouillé" -> "Non ouvert"; search, filters, CSV export. |  | Validated | Done | Columns "Score du quiz" (80 % · Réussi) and "Tentatives"; "Verrouillé" renamed "Non ouvert" on the teacher side; search, status filter, CSV export.
TCH-3 | Teacher > class > Élèves | Teacher | Major | No row action (open quiz, allow a retry, change class). | Row menu + checkboxes for bulk "Ouvrir le quiz". |  | Validated | Done | Row menu (open the quiz, allow a new attempt, change class) and checkboxes with bulk "Ouvrir le quiz". All logged.
TCH-4 | Teacher > class > Élèves | Teacher | Major | No "Ajouter un élève" although the school setting "Délégation aux enseignants" is ON. | Button "Ajouter un élève" (pop-up) shown only when delegation is on. |  | Validated | Done | Button "Ajouter un élève" (pop-up), shown only when the delegation setting is on.
LIVE-1 | Teacher > Sessions en direct | Teacher | Minor | Session cards are clickable DIVs (no keyboard access, no visible action). | Real link + "Voir en direct" button. |  | Validated | Done | Session cards use a real link on the name and a "Voir en direct" button (keyboard accessible).
LIVE-2 | Teacher > live view | Teacher | Major | No live metrics. | Side panel: step n / 13, errors, hints used, elapsed time, steps done. |  | Validated | Done | Side panel: step n / total, errors, hints used, elapsed time, steps done. Figures are demo data.
LIVE-3 | Teacher > live view | Teacher | Minor | The hint overlay covers the scene and overlaps the badge "L'élève voit dans son casque". | Move the overlay out of the scene (dedicated bar). |  | Validated | Done | The hint and the "what the student sees" badge moved to a dedicated bar above the scene.
LIVE-5 | Teacher > Sessions en direct | Teacher | Minor | No filter (class, Web / VR). | Add filters and a count. |  | Validated | Done | Class and Web / VR filters with a session count.
AUD-1 | Audit log (Client Admin) | Client Admin | Minor | Stored values stay in English in the FR UI ("Class 2A · 1 student(s)", "Startup Procedure"). | Store codes / ids and translate at display time. |  | Validated | Partial | Audit entries now store codes / ids and are translated at display time (school-side actions, seeds, SQL runs). COMIM licence, feature and establishment actions still write a free-text target.
AUD-2 | Audit log (both) | Client Admin / COMIM Admin | Minor | Rows are not clickable; targets are plain text. | Target = link to the user / class / headset page (ADM-4). To be done together with the audit-log UI (see AUD-4 / AUD-5). | https://claude.ai/artifact/LrdaNRAZ64k2KKeh9nBUJi | Validated | Done | Target is a link to the user / class / headset / question / settings page (Client Admin) or to the establishment sheet (COMIM Admin). Entries are not otherwise clickable.
SET-1 | Client Admin > Paramètres | Client Admin | Major | "Retirer" on a track has no guard (not clicked during the test). | Block the removal of a track while classes / students use it (message naming the classes). |  | Validated | Done | Removing a track is blocked while classes use it, with a message naming the classes and the number of students.
SET-2 | Client Admin > Paramètres | Client Admin | Minor | Delegation and tracks save instantly without feedback; "Enregistrer" covers only the school block. | Toast "Paramètres enregistrés" for every change. |  | Validated | Done | Toast "Paramètres enregistrés" for every change (school block, delegation, tracks); each change is also logged.
SET-3 | Client Admin > Paramètres | Client Admin | Minor | Mixed languages in school data ("Port de Casablanca, Morocco"), track names in English in FR. | Translate / harmonise. |  | Validated | Partial | Address harmonised ("Port de Casablanca, Maroc"); track and class names are shown in French on Settings, Users, Classes, question bank, admin detail pages, the teacher class header and live sessions. Other screens still show the stored English class names.
VR-4 | VR (all modules) | Student | Info | Every VR module is the same 2D web screen inside a VR frame (top bar with headset id and hand-tracking %, bottom hint bar); no immersive 3D scene. The test was a browser simulation: hand tracking, depth, comfort, spatial audio and real target sizes were not testable. | All web findings (3D, zoom, Repair, Identification, results, Exploded view) apply to VR; the real VR delivery is the 3D / XR package. |  | Validated | Not done | Information row. The VR modules are still the web screens in a VR frame; the web fixes above apply to them. The immersive scene is the 3D / XR package.
PREV-5 | Course preview | Teacher | Minor | Catalogue preview: no banner; its "Course Menu" breadcrumb goes to My Classes. | Same preview chrome (see PREV-1). |  | Validated | Done | Catalogue preview now has the preview banner and its breadcrumb goes back to "Aperçu du cours".